## Read Me
Frankie BOSS Build Plan
Mapping, governed QSV attachment and rolling forecast software built. Production B2_GATED remains incomplete.
CURRENT STATUS: best comparable candidate selection and all-horizon revisions are tested. Native forecast heads and Frankie integration remain pending. Training, market-data runs and evaluation remain parked.
Build families |  | System arms |  | Dipole controls | Final target
4 |  | 8 |  | 6 | B2_GATED
How to read this workbook
Build Plans | The four design families: A protected Frankie, B0 native fixed depth, B1 native recurrent, and B2_GATED final candidate.
Components | Every BOSS/live-stack piece, what it can do now, the intended role, authority, prohibited behavior, dependency, and next work.
Roadmap | The brownfield order of work. This order protects the current Frankie and prevents Granite/dipole work from hiding missing B1 foundations.
Experiment Arms | The eight clean/memory system locks and six D0-D5 dipole controls. These matrices answer different scientific questions.
Gates | Stop conditions for implementation, data, causality, dipole, Granite, blind evaluation, licensing, and automated execution.
Sources | Repository and official external sources used to populate the workbook.
Status language
Built / preserve | Executable evidence exists; preserve or import carefully. | Specified - not built | The role is accepted but implementation is missing.
Partial | Some source or tests exist, but the brownfield production seam is incomplete. | Built - repair required | Code exists, but a known defect/gap invalidates result-bearing use.
External gate | Provider/API/license exists outside the repository; acceptance is not yet proved. | Blocked | A required proof currently fails or depends on an unresolved external answer.
Important | 871 synthetic checks passed; 1 CUDA-only skip. Includes 82 new forecast checks. Counts overlap earlier focused suites and must not be added. | Live authority | Only native causal B1 plus deterministic safety policy may eventually influence orders.
Candidate | Design fit / 100 | Prior readiness / 100
B0 fixed native | 73 | 75
B1 native recurrent | 85 | 15
B2 Granite hot path | 66 | 5
B2_GATED | 92 | 10
Prior engineering scores are historical estimates and were not recalculated. They are not current acceptance or predictive evidence. See Preservation Audit.
COMPLETED SOFTWARE: exact native mapping, context receipts, C15R2 attachment, governed QSV attachment, internal reliability diagnostics and retry-safe rolling revisions. No trained forecast or production gate is claimed.

## Build Plans
Four BOSS Build Families
Each row separates what the plan is for, what is already possible, what is still missing, and which component is allowed to be authoritative.
Plan | Family | Build name | Primary function | What runs | Intended role | Reasoning layer | Granite role | ReFRAG/QSV role | Dipole role | Current capability | Current status | Design fit | Readiness | Key gap | Live authority
1 | A | Protected Frankie baseline | Preserve the current Frankie controller and measure clean versus Memory A behavior without BOSS. | Current Frankie, existing reasoning/orchestration, clean or protected A-memory. | Scientific baseline, preservation oracle, and safe fallback. It is not the final BOSS predictor. | Existing Frankie reasoning only; no BOSS recurrence. | None. | Not active in this baseline. | None. | S127 proves the current A-memory principal run. A-clean contracts exist separately. | Built - preserve |  |  | No BOSS market state/reasoning layer and no automated-execution authority. | Frankie controls only its existing output path; no model may submit orders.
2 | B0 | Fixed-depth native BOSS | Provide the causal typed-market baseline and a control for all later reasoning additions. | Native trunk, one temporal graph branch, within-sequence gated delta memory, ReFRAG/QSV seam, BLD-1 projector. | Control architecture. It proves whether the native BOSS representation adds value before recurrence or Granite. | Fixed number of trunk layers. GatedDeltaCell tracks sequence time but is not whole-representation reasoning. | None. | Optional, named, masked, and exactly ablatable QSV input. | Training experiment can attach, but it is not required for B0 inference. | Exact native mapping, context receipts and C15R2 attachment built; synthetic checks pass. Production and experiment runs remain parked. | Partial | 73 | 75 | Connect through the protected Frankie interface, prove BOSS-disabled identity, complete feed conformance and production wiring, and validate throughput/context length. | Native typed state is authoritative; B0 remains a control after B1 exists.
3 | B1 | Recurrent native BOSS | Add repeated reasoning over the entire BOSS representation without depending on an LLM. | B0 representation plus shared-weight whole-representation recurrence and a bounded halting policy. | Required market-authoritative reasoning core and no-Granite comparison. | Repeated full-state reasoning with explicit state, iteration limit, halting, and receipts. | None. | Same governed QSV surface as B0; no duplicate registry. | Validated auxiliary supervision may train representation, but does not run as an authority at inference. | Native mapping, context/teacher receipts, governed QSV attachment and additive rolling forecast software are built. Native forecast heads and Frankie wiring remain pending. | Partial | 85 | 15 | Build native forecast heads and protected Frankie wiring. Complete QSV producer/feed conformance and throughput/context validation. Runs remain parked. | B1 is the required native authority in the final design.
4 | B2 | B2_GATED final candidate | Combine the native B1 core with bounded Granite 4.2 8B reasoning assistance while retaining ReFRAG and tested dipole supervision. | B1 plus deterministic state serializer, frozen Granite checkpoint, closed output parser, disagreement policy, shadow receipts, and safe fallback. | Fourth and final target. Granite begins as a shadow teacher/critic and can earn a bounded decision-affecting role only through tests. | B1 remains authoritative. Granite critiques or teaches through a closed schema. | Shadow-only initially; no broker tools, market-truth authority, memory writes, or blocking dependency. | Owns named QSV/operator governance and exact ablation. | D5 aligned dipole is a falsifiable training arm only after D0-D4 controls are valid. | Mapping, QSV attachment, internal reliability and all-horizon selection/revision software are built. The complete production B2_GATED system remains unfinished. | Partial | 92 | 10 | Native forecast heads, Frankie compatibility, production inputs/QSV producer, six teacher columns, Granite serving and experiment orchestration remain. Execution is later. | Native B1 state remains authoritative. Granite can never directly submit an order.

## Components
BOSS Component Role Matrix
The most important sheet: current behavior and intended behavior are separate columns so an unfinished component is never mistaken for a working capability.
ID | Area | Component | Function now | Intended role | Current capability | Current status | Required next work | Authority in B2 | Must never do | Used by plans | Build phase | Dependency | Source evidence
C01 | Controller | Current Frankie | Runs the existing role/orchestration and memory-use contract. | Remain the protected controller that receives only the governed BLD-1 projection from BOSS. | Built and evidenced by the frozen Sunday run. | Built - preserve | Connect the new BOSS through the existing protected interface and prove BOSS-disabled behavior remains byte-identical. | Final controller around BOSS output, not raw market reconstruction. | Must not be overwritten wholesale by the recovered branch or exposed to Step-1 answers. | A, B0, B1, B2 | 0 - Preserve | Current branch health | S127 handoff and frozen principal run
C02 | Memory | Memory A | Supplies the protected learned-output package to the memory arms. | Remain immutable experimental evidence and the only difference between clean and memory arms. | Built and frozen. | Built - preserve | Use a hash-bound copy/reference; write all new findings to a separate namespace. | Read-only input to memory arms. | Granite or BOSS must never rewrite it directly. | A-memory, B0-memory, B1-memory, B2-memory | 0 - Preserve | Memory manifests and hashes | Current branch memory contracts
C03 | Data | Live/historical MBO source adapter | No accepted production BOSS adapter exists on the current lineage. | Translate original order-level feed messages without weakening identity, timing, sequence, or event groups. | Vendor candidates identified; semantics not proved. | External gate | Complete feed conformance and production wiring under the existing source/retention contracts. Market-data runs remain parked. | Source translator only. | Must not collapse MBO to top of book or MBP-only input. | B0, B1, B2 | 3 - Input | DTN/CME contract and trial | 04 vendor assessment
C04 | Data | Causal group stream | Orders raw events into governed receive-time groups for Frankie. | Feed every BOSS state at the same causal group boundary in ts_recv_ns order. | Built in the current Frankie lineage. | Built | Expose an additive typed interface to the BOSS input builder and preserve existing receipts. | Causal ordering authority. | Must not reorder on exchange timestamp or reveal a future group. | A, B0, B1, B2 | 3 - Input | Raw MBO and current contracts | Current causal stream modules
C05 | Data | Causal packet | Causal packet v2 retains every known as-of version and exact immutable payloads. | Be the immutable audit boundary passed into every BOSS arm. | Full records reach feature functions; current-fact resolution is explicit. Clock defects and unknown completeness propagate. | Built | Native context packets bind exact records, adapter metadata, defects and source prefixes. | Audit and provenance authority. | Must not contain future outcomes, another arm's result, or hidden defaults. | B0, B1, B2 | 3 - Input | Causal group stream | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C06 | Data | Production BOSS input builder | Opt-in ContextSessionRunner maps the complete journal to exact native context tensors. | Construct numeric, categorical, graph, QSV, masks, labels, and teacher targets from one hash-bound causal prefix. | Exact native fields and governed QSV artifacts reach native computation with receipt/retry binding. Production producer/feed validation remains open. | Built - software | Complete production feed wiring and conformance; validate throughput and provisional T_CTX=4096. Operational runs remain parked. | Only approved entry into the BOSS model. | Must not hand-build tensors or fabricate unavailable values. | B0, B1, B2 | 3 - Input | Causal packet and registries | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C07 | Representation | Numeric projector | Numeric projection now has per-field availability and a separate missingness contribution. | Remain a deterministic typed feature path shared by B0, B1, and B2. | Known coordinates in partial rows retain gradient paths; no raw normalization added. | Built | Built: exact sign/high32/low32 float64 views plus original typed byte tensors. | Native representation component. | Must not infer missing values as zero. | B0, B1, B2 | 4 - Native core | Input schema | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C08 | Representation | Categorical embeddings | Categorical encoder requires exactly every configured column and supports per-field missingness. | Preserve stable vocabularies and unknown/missing handling across every arm. | Extra columns raise explicitly; absent fields do not suppress the remaining row. | Built | Built: exact identity bytes and UNKNOWN preservation; undeclared fields fail explicitly. | Native representation component. | Must not silently remap categories between runs. | B0, B1, B2 | 4 - Native core | Input schema and registries | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C09 | Representation | TemporalGraphBranch | Temporal ancestry rejects future parents and invalid negative indices. | Supply a single governed graph contribution to the complete representation. | Every submitted row remains in the ordered sequence; causal graph validation is explicit. | Built | Built: causal in-context order links scoped by exact publisher/instrument/order identity. | Native graph authority. | Must not be duplicated per layer or supplied with future ancestry. | B0, B1, B2 | 4 - Native core | Parent/graph input | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C10 | Representation | GatedDeltaCell | Existing learned delta-memory arithmetic is retained. | Remain temporal memory inside the native representation. | Existing delta memory operates over the declared context. Complete history is journaled and processed by the attached teacher. | Built | Keep retention and model context distinct; provisional T_CTX is 4096. | Temporal feature memory only. | Must not be described as B1 reasoning depth. | B0, B1, B2 | 4 - Native core | Sequence representation | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C11 | Reasoning | B0 fixed-depth trunk | V2 defaults restored: window=128, use_qsv=False. V1 control source is pinned. | Remain unchanged as the control beside B1. | Six preservation checks prove pinned V1/V2 bit-identical B0 fixtures. NativeTrunk is additive. | Built - software | Production integration is separate; retain V1 control and exact weight/config identities. | Native B0 control authority. | Must not be mutated into B1 and thereby destroy the control. | B0, B1 base, B2 base | 4 - Native core | C07-C10 | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C12 | ReFRAG | QSV/operator registry | QSV is optional, disabled by default, named and exactly ablatable. | Remain the sole authority for QSV names and ordering used by BOSS. | Registered QSV vectors and coordinate masks reach native/B1 computation with source-prefix and trusted artifact binding. | Built | Governed QSV artifact attachment to the native runner is built. Complete producer-side wiring, conformance and throughput validation. | Registry authority. | BOSS must not create a duplicate private QSV registry. | B0, B1, B2 | 4 - Native core | ReFRAG package | QSV_CONTEXT_HANDOFF_20260914.md; commit 25db5c8b
C13 | ReFRAG | QSV mask and exact ablation | Numeric, categorical and QSV missingness is field-level. | Make QSV present/missing/ablated states explicit in training and inference. | Unavailable values are explicit; available coordinates remain active. | Built | Enabled artifact masks and exact ablation are tested. Preserve zero/missing/ablated distinctions through production producer and training integration. | Input-state authority. | Must not confuse present zero with missing or ablated. | B0, B1, B2, D0-D5 | 5 - Teacher repair | C06 and C12 | context_qsv.py; tests/test_context_qsv.py; commit 25db5c8b
C14 | Dipole | Dipole target schema | Existing C14 19-column DipoleTarget restored downstream of raw evidence. | One causal teacher artifact per context cutoff, with its own prefix and normalizer identity. | C15R2 attachment built; six unbuilt B2/C1 columns remain explicitly ABLATED. | Built | Six B2/C1 target columns remain unimplemented and explicitly ABLATED. Complete those columns and paired experiment integration. | Training-target contract only. | Must not use future events, realized outcomes, or another arm's prediction. | D2-D5; training for B1/B2 | 5 - Teacher repair | C06 and ReFRAG registry | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C15 | Dipole | C15 complete native evidence | Complete evidence journal plus downstream C15R2 teacher attachment. | Retain and deliver every raw event, order history, field, FIFO level and integrity diagnostic; prove actual model use. | All prefix records processed; authoritative book/ranks, invalid states and per-cutoff targets verified. | Built - software | C15R2 attachment is complete. Six B2/C1 target columns and paired experiment integration remain pending. Preserve exact raw evidence. | Training-data construction only. | Must not leak October 4/5 outcomes into fitting. | D2-D5; training for B1/B2 | 5 - Teacher repair | C03-C06, C14, and additive record-hook seam | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C16 | Dipole | TeacherHead | Projects hidden states into auxiliary-target space and adds MSE auxiliary loss. | Measure whether auxiliary representation supervision improves predeclared BLD objectives. | Executable PyTorch harness with smoke tests. | Built | Bind output width/names to C14 and extend evaluation beyond binary p_up. | Training-only head. | Must not become execution or market-truth authority. | D2-D5 | 5 - Teacher repair | B0/B1 hidden state and target schema | frankie_boss/teacher.py
C17 | Dipole | plain_aux control | Uses a fixed random projection of numeric inputs, independent of aligned dipole target values. | Provide a credible generic auxiliary-task control independent of aligned dipole correspondence. | Existing corrected control and characterization tests pass. | Built | Preserve the existing projection and tests; prove paired production-run integration and identity. | Falsification control only. | Must not retain target-derived information while claiming to be an input-only control. | D2 | 5 - Teacher repair | C14-C16 | teacher.py; tests/test_teacher_controls.py; R3 addendum §6
C18 | Dipole | Shuffled and random controls | Uses a Sattolo derangement and CPU-generator random targets with declared masks. | Show whether aligned dipole structure beats matching marginals and generic noise. | Existing correspondence and RNG tests pass; CUDA-only check skipped in CPU environment. | Built | Preserve existing controls; prove production correspondence/mask identity and device behavior where required. | Falsification controls only. | Must not silently preserve the original correspondence. | D3, D4 | 5 - Teacher repair | C14-C16 | teacher.py; tests/test_teacher_controls.py; R3 addendum §6
C19 | Reasoning | B1 recurrent controller | Unchanged B1 supports pinned V1, preserved V2 and opt-in NativeTrunk. | Reprocess the complete native representation with shared weights across bounded reasoning steps. | 98 dual-lineage B1 acceptance/regression checks pass; native context/B1 integration also passes. | Built - software | Connect through the protected Frankie interface and prove BOSS-disabled identity. Preserve both trunk controls; result runs remain parked. | Required market-authoritative reasoning core. | Must not depend on Granite availability. | B1, B2 | 6 - B1 | B0 representation | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C20 | Reasoning | B1 halting policy | Fixed/convergence reasoning depth remains an explicit compute policy. | Bound reasoning cost and determine when recurrence stops without outcome access. | Every declared context row is processed; finite recurrence and model context are explicit. | Built - software | Retain tested halting/receipt contract; no production or result run. | Compute-governance authority. | Must not wait indefinitely or tune halting on blind outcomes. | B1, B2 | 6 - B1 | C19 | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C21 | Granite | Deterministic state serializer | State serializer v2 round-trips exact finite numerics and their int/float types. | Be the only answer-walled bridge from B1 state to Granite. | Large integers, signed zero and independent-clock times survive. Extra QSV entries, underflow and mislabeled schemas fail explicitly. | Partial | Wire serving source-state binding to the native B1 state and exact serializer. Preserve the answer wall. | Serialization authority only. | Must not include outcome, other-arm output, broker state, credentials, or ungoverned memory. | B2 | 7 - Granite shadow | C05-C13 and B1 state | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C22 | Granite | Granite 4.2 8B checkpoint/runtime | No approved model download or serving path is wired into Frankie/BOSS. | Provide frozen generic reasoning assistance as a shadow teacher/critic. | Official checkpoint exists under Apache 2.0; repository integration is absent. | Specified - not built | Pin checkpoint, tokenizer and runtime settings; wire serving and verify identity. Model runs remain parked. | Shadow critic initially. | Must not reconstruct market truth, write memory, hold credentials, or submit orders. | B2 | 7 - Granite shadow | C21 and serving infrastructure | 02 Granite assessment
C23 | Granite | Closed Granite parser, prompt and receipt | Approved Granite output/prompt V1 caps and nonempty hypotheses restored. | Closed bounded assistance output, exact references and evidence verdict; state serialization stays V2. | 195 focused Granite/precision checks pass. No model/provider run. | Partial | Parser/prompt contracts are built. Complete pinned serving, source-state binding and timeout handling. | Model-output validation authority. | Must not accept free-form order side, size, price, or broker command. | B2 | 7 - Granite shadow | C21-C22 | research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md
C24 | Granite | B2 disagreement/fusion policy | No decision-affecting fusion exists. | Preserve B1 and Granite independently; initially record disagreement without altering live behavior. | Missing. | Specified - not built | Implement shadow disagreement policy and timeout fallback while preserving native B1 authority. | Native B1 wins every invalid/unavailable case. | Granite must not override causal state or become a blocking dependency. | B2 | 7 - Granite shadow | C19-C23 | 01 and 02 decisions
C25 | Output | BLD-1 projector | Protected BLD-1 projector is unchanged. A separate additive layer selects comparable candidates and journals all-horizon revisions. | Remain the only narrow BOSS-to-Frankie learned-output seam. | 82 synthetic forecast checks pass. No categorical score floor. Native forecast generation and protected integration are not built. | Partial | Build native gap/path/endogenous-time heads. Resolve legacy confidence-enum compatibility without labeling every winner high. Prove disabled identity. | Output-interface authority. | Must not pass raw Granite scores or hidden extra heads. | B0, B1, B2 | 4 - Native core | BOSS heads and Frankie contract | ROLLING_FORECAST_BUILD_HANDOFF_20260914.md; commit ccc7159d
C26 | Experiment | Checkpoint and resume | Journal-verified context restore binds exact inputs, source membership, teacher and model identity. | Guarantee continuous replay equals restored replay for every arm. | Context restart plus durable forecast revisions and whole-refresh intent binding are tested. Changed source/model/settings or partial-retry scope reject. | Built - software | Wire the native producer using actual content-derived generation hashes. Add governed checkpoint recovery and external delivery separately. | Experiment continuity authority. | Must not resume with changed data, model, registry, or thresholds. | B0, B1, B2, D0-D5 | 8 - Evaluation | All frozen identities | context_session.py; rolling_forecast.py; forecast_refresh.py
C27 | Experiment | Eight-arm lock and single-reveal scorer | Accepted matrix is documented; no completed B0/B1/B2 result program exists on current Frankie. | Run A/B0/B1/B2 clean and memory arms independently and reveal held-out scores once. | Specified; current A evidence exists separately. | Specified - not built | Complete immutable arm locks, paired controls, frozen outputs and single-reveal scoring. Training, market-data runs and OSS evaluation remain parked. | Scientific comparison authority. | Must not let one current arm read another or tune on October 4/5. | A, B0, B1, B2 | 8 - Evaluation | C06-C26 | Accepted raw-MBO benchmark handoff
C28 | Safety | Deterministic risk gate | No BOSS live-order gate is implemented in this tranche. | Convert only hash-bound model intent into allowed instrument, size, price, session, exposure, and loss-bounded instructions. | Specified in the live-stack decision. | Specified - not built | Implement separately after model evaluation; test stale state, position, loss, and kill conditions. | Sole pre-order policy authority. | No LLM may bypass it or change an intent after approval. | Later live B1/B2 | 10 - Execution | Validated model output and account state | 05 execution assessment
C29 | Safety | Order ledger and reconciler | No shared durable BOSS execution ledger exists. | Record intent before send; reconcile acknowledgments, fills, cancels, rejects, timeouts, and account state. | Specified only. | Specified - not built | Build an outbox/state machine and ambiguous-timeout recovery before production credentials. | Execution-state authority. | Must not blindly retry a timed-out submission. | Later live B1/B2 | 10 - Execution | C28 and provider APIs | 05 execution assessment
C30 | Execution | Tastytrade adapter | Official API/sandbox exists; no governed Frankie adapter is recorded here. | Execute approved futures/options intents for the user's account. | External API available; internal adapter missing. | External gate | Verify permissions, sandbox mechanics, order lifecycle, fees, and automated-use terms; then implement typed adapter. | Venue translation only. | Must not receive free-form model text or invent retry semantics. | Later live B1/B2 | 10 - Execution | C28-C29 and broker approval | Tastytrade official documentation
C31 | Execution | Kalshi adapter | Official REST/WebSocket/FIX and demo environment exist; no governed Frankie adapter is recorded here. | Execute approved event-contract intents for the user's account. | External API available; internal adapter missing. | External gate | Verify account/API permissions, rate/fee rules, client IDs, reconciliation, and demo behavior; implement typed adapter. | Venue translation only. | Must not receive free-form model text or share CME data outside its license. | Later live B1/B2 | 10 - Execution | C28-C29 and venue approval | Kalshi official documentation

## Roadmap
Brownfield Build Roadmap
The sequence is deliberate: preserve first, prove B0, build native B1, repair the dipole experiment, then add Granite shadow reasoning and only later execution.
Seq | Phase | Objective | Primary deliverables | Evidence required | Protected boundary | Current status | Owner lane | Depends on
0 | Preserve | Freeze the known-good current Frankie and Memory A boundary. | Verified parent SHA, frozen Sunday artifact, memory hashes, no-rerun rule. | Hash and manifest verification. | No code or data rewrite in frozen directories. | Complete | Current Frankie lineage | None
1 | Current-line health | Close active S128 result self-hash/cadence defects before cloning the integration base. | Correct result identity and proof without relaxing validation. | Existing regression and new defect test pass. | Do not repair by weakening the check. | Open | Current Frankie lineage | Stage 0
2 | Clone | Create an isolated integration branch from the then-current verified Frankie tip. | Parent SHA record and untouched protected baseline. | Branch ancestry and clean diff. | Memory A remains read-only. | Not started | Integration | Stage 1
3 | Import | Bring B0/ReFRAG foundations into the clone additively. | Selected modules, tests, registry identities, restart contracts. | File-by-file brownfield comparison and preservation suite. | No wholesale overwrite of active Frankie files. | Not started | Integration | Stage 2
4 | Input | Complete production input conformance and wiring; validate throughput and provisional context length. | Exact native mapping and journal-backed context runner built. Production feed conformance, throughput and T_CTX=4096 validation remain pending. | 49 native/teacher/session checks plus existing evidence/history checks; production data conformance remains. | No MBP/top-of-book substitute, no future data, and no change to current Frankie inputs/calculations/planes. | Partial | Data/BOSS | Stage 3 and vendor PoC
5 | B0 | Connect new BOSS through the existing protected interface and prove BOSS-disabled identity. | B0 adapter, BLD-1 projection, disabled identity mode. | BOSS-off output is byte-identical; B0 tests pass. | B0 remains unchanged as the control. | Not started | BOSS native | Stage 4
6 | B1 | Integrate the built recurrent B1 through the protected interface. | B1, governed QSV attachment and rolling forecast software are built. Native forecast heads, protected Frankie integration and QSV producer wiring remain. | 871 broad synthetic checks pass with 1 CUDA-only skip. Includes 82 forecast checks; no operational or accuracy claim. | Granite is not required for B1 availability. | Partial | BOSS native | Stage 5
7 | Dipole | Preserve existing dipole schema/controls and complete the causal training-data path. | C15R2 teacher attachment built. Six B2/C1 columns remain unimplemented/ABLATED; paired experiment integration remains pending. | All controls differ as declared and use identical paired conditions. | No held-out tuning; teacher remains training-only. | Partial | Teacher experiment | Stages 4-6
8 | Granite | Wire Granite 4.2 8B as an independent B2 shadow lane. | Parser/prompt contracts built. Pin checkpoint/runtime and wire serving, source-state binding, timeout handling and shadow disagreement policy. | 195 focused checks; Granite serving/fusion remains separate. | No broker credentials, memory writes, or live blocking. | Partial | Granite shadow | Stage 6
9 | Warmup | Use October 1 and 3 for mechanics, fitting, and validation. | Parked. Teacher normalizer restored downstream of exact raw evidence. T_CTX=4096 is provisional; no mechanics or training run. | All warmup gates pass without rewriting the Sunday artifact. | No headline claim from warmup days. | Not started | Evaluation | Stages 5-8
10 | Blind | Run October 4 and 5 as paired held-out evaluation. | Freeze scoring quantities, exclusions, paired replay/horizon groups and output hashes before one reveal. Full arm orchestration remains unbuilt. Runs stay parked. | Independent arm locks and post-freeze scoring. | No arm sees another current arm or outcome before lock. | Not started | Evaluation | Stage 9
11 | Forward shadow | Test live data and system behavior without order submission. | Latency, coverage, calibration, failure, disagreement, and cost evidence. | Multiple sessions reproduce the claimed benefit. | Safe abstention on invalid state. | Not started | Operations | Stage 10 and data license
12 | Execution | Add deterministic risk, ledger, tastytrade, and Kalshi adapters. | Later work: deterministic risk controls, durable order ledger/reconciliation and governed Tastytrade/Kalshi adapters. | Failure drills and separate user live-capital authorization. | No model directly submits or retries an order. | Not started | Execution | Stage 11 and licensing

## Experiment Arms
System and Dipole Experiment Arms
The eight A/B0/B1/B2 locks test architecture and memory. D0-D5 separately test whether aligned dipole supervision adds unique value beyond QSV and auxiliary controls.
Matrix | Arm | Controller | Memory | Native reasoning | Granite | QSV | Auxiliary target | Control identity | Role/purpose | Current readiness | Question answered
System | A-clean | Current Frankie | Clean | Off | None | None | Not active | None | Protected no-BOSS baseline. | Baseline contract exists; this workbook does not claim a new run. | What does current Frankie do without learned Memory A?
System | A-memory | Current Frankie | Memory A | Off | None | None | Not active | None | Protected current-memory baseline. | Frozen Sunday principal evidence exists. | What does the same Frankie do with the protected memory package?
System | B0-clean | B0 | Clean | Fixed depth | None | Optional/ablatable | Optional training | Controlled separately | Native BOSS causal baseline without recurrence or Granite. | Core code exists; integration and result run missing. | Does fixed-depth native BOSS add value over A?
System | B0-memory | B0 | Memory A | Fixed depth | None | Optional/ablatable | Optional training | Controlled separately | Same B0 with only Memory A changed. | Core code exists; integration and result run missing. | Does memory change B0 under an otherwise identical lock?
System | B1-clean | B1 | Clean | Whole-state recurrent | None | Same as B0 | Validated training only | Controlled separately | Native reasoning candidate without Granite. | Parked. Exact native mapping and C15R2 attachment built; production experiments remain separately authorized. | Does recurrent reasoning beat fixed-depth B0?
System | B1-memory | B1 | Memory A | Whole-state recurrent | None | Same as B0 | Validated training only | Controlled separately | Same B1 with only Memory A changed. | Parked. Exact native mapping and C15R2 attachment built; production experiments remain separately authorized. | Does memory add value once native recurrence exists?
System | B2-clean | B2_GATED | Clean | B1 authoritative | Granite shadow/critic | Same as B1 | Validated training only | Controlled separately | Full final candidate without Memory A. | Parked. Exact native mapping and C15R2 attachment built; production experiments remain separately authorized. | Does Granite add value over identical B1 without becoming authority?
System | B2-memory | B2_GATED | Memory A | B1 authoritative | Granite shadow/critic | Same as B1 | Validated training only | Controlled separately | Full final candidate with protected Memory A. | Parked. Exact native mapping and C15R2 attachment built; production experiments remain separately authorized. | Does the complete candidate benefit from protected memory?
Dipole | D0 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | Off or exact ablation | None | None | Clean native floor. | Requires production runner. | What happens with neither QSV contribution nor auxiliary target?
Dipole | D1 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | On | None | None | QSV-only baseline. | Existing mask code/tests pass; production runner and preservation proof pending. | What does QSV add without any auxiliary loss?
Dipole | D2 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | On | Corrected plain auxiliary | Fixed random input projection | Generic learnable auxiliary-gradient control. | Corrected plain_aux code/tests pass; paired production proof pending. | Does any ordinary auxiliary task explain the gain?
Dipole | D3 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | On | Shuffled dipole | Correspondence destroyed | Marginal-preserving correspondence control. | Existing derangement tests pass; production correspondence proof pending. | Does aligned correspondence matter?
Dipole | D4 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | On | Random | Dense noise | Noise/regularization control. | CPU RNG tests pass; CUDA check skipped; production/device proof pending. | Does generic noise explain the gain?
Dipole | D5 | Same chosen native model | Fixed for comparison | Unchanged | Fixed/off by matrix | On | Aligned dipole | Real target | Hypothesis arm. | Causal teacher attachment built and checked. Paired training and blind results remain parked. | Does aligned dipole beat D0-D4 by a practical, stable margin?

## Gates
BOSS Promotion Gate Registry
A required gate is a stop condition. OPEN means work remains; BLOCKED means a known defect or external dependency currently prevents a valid result.
Gate | Category | Requirement | Applies to | Passing evidence | Work status | Required | Gate state | Failure action | Owner lane
G01 | Preservation | Frozen Sunday artifact and Memory A remain unchanged. | All | Hash/manifest comparison | Complete | YES | COMPLETE | Stop on any difference. | Current lineage
G02 | Current health | S128 result self-hash and cadence defects are closed without weakening checks. | Integration base | Regression tests and recomputed identity | Open | YES | OPEN | Do not clone an unhealthy base. | Current lineage
G03 | Branching | Integration clone records exact parent SHA after current work is complete. | B0-B2 | Remote ancestry | Not started | YES | OPEN | Abort on head race. | Integration
G04 | Preservation | BOSS-disabled behavior is byte-identical to protected Frankie. | B0-B2 | Before/after bundle hash | Not started | YES | OPEN | Reject integration. | Integration
G05 | Data | Input retains original order identity, actions, side, price, quantity, sequence, timestamps, groups, and recovery. | B0-B2 | Vendor PoC plus adapter conformance | External | YES | BLOCKED | Reject source or adapter. | Data
G06 | Causality | Every state uses ts_recv_ns and contains no future event/outcome. | All B arms | Causal context/restart checks pass. Timing-label resolution still requires measured timestamp resolvability; interarrival gaps alone are not jitter. | Partial | YES | OPEN | Invalidate run. | Data
G07 | Book | Full book, FIFO, queue position, volume ahead, age, and lifecycle are not collapsed. | All B arms | Existing full-book/FIFO evidence retained; exact native inverse and teacher book reads checked. | Partial | YES | OPEN | Invalidate run. | Data
G08 | B0 | Recovered fixed-depth B0 and ReFRAG tests pass on current integration branch. | B0-B2 | Pinned V1/V2 B0 preservation: 6 checks pass. Production integration remains separate. | Partial | YES | OPEN | Stop B1 work. | BOSS native
G09 | B1 | Whole-representation B1 runs on both control lineages and opt-in native context. | B1-B2 | 98 dual-lineage B1 checks plus native context integration pass; no production or result claim. | Partial | YES | OPEN | B1/B2 unavailable. | BOSS native
G10 | B1 | Halting is bounded, receipted, and outcome-independent. | B1-B2 | Dual-lineage halting/receipt checks pass; native retry and model identity bound. | Partial | YES | OPEN | Reject B1/B2 run. | BOSS native
G11 | Dipole | Exact native input mapping and separate C15R2 causal teacher attachment preserve raw evidence. | D2-D5 | 19-column attachment built with explicit six ablations, missing/invalid states and per-cutoff hashes. Synthetic checks pass. | Partial | YES | OPEN | No dipole run. | Teacher
G12 | Dipole | plain_aux matches its declared fixed random input projection and contains no aligned target information. | D2 | Existing tests/test_teacher_controls.py pass; production integration/preservation pending. | Partial | YES | OPEN | Invalidate auxiliary comparison. | Teacher
G13 | ReFRAG | qsv_mask reaches training and inference; zero, missing, and ablated remain distinct. | B0-B2, D0-D5 | Governed QSV artifacts/masks reach native B1 with causal source and retry binding; 11 focused checks pass. Producer/training/throughput proof remains. | Partial | YES | OPEN | Invalidate QSV result. | Teacher/BOSS
G14 | Dipole | Shuffled control always destroys correspondence; random control is deterministic per frozen seed/device. | D3-D4 | Existing derangement/CPU RNG tests pass; CUDA check skipped; production/device proof pending. | Partial | YES | OPEN | Invalidate dipole verdict. | Teacher
G15 | Objectives | Evaluate declared forecasts, full reliability/coverage curves, abstention, latency and defects. Test confidence's added information; not p_up alone. | B0-B2, D0-D5 | Design plus 39 internal reliability and 43 selection/revision/refresh checks built. Full G15 metric schema and empirical acceptance remain open. | Partial | YES | OPEN | No promotion claim. | Evaluation
G16 | Granite | Exact Granite checkpoint, tokenizer, quantization, runtime, mode, sampling, and license are frozen. | B2 | Identity receipt | Not started | YES | OPEN | Reject Granite output. | Granite
G17 | Granite | Serializer preserves required numeric/graph/mask relationships and excludes answers, outcomes, broker data, and credentials. | B2 | Exact state serialization V2 retained; approved bounded Granite V1 contracts pass focused checks. | Partial | YES | OPEN | Keep Granite disconnected. | Granite
G18 | Granite | Replicated inference quantifies output variance under the chosen decoding recipe. | B2 | Predeclared repeated draws and hashes | Not started | YES | OPEN | Do not use as teacher label. | Granite
G19 | Granite | Timeout, malformed output, hash mismatch, and disagreement leave B1 running or safely abstaining. | B2 | Failure drills | Not started | YES | OPEN | Granite remains shadow/off. | Granite
G20 | Experiment | All eight clean/memory arms use identical allowed locks except the declared factor. Declare horizon/replay pairing and grids before outcomes. | System matrix | Lock cross-check | Not started | YES | OPEN | Invalidate comparison. | Evaluation
G21 | Experiment | D0-D5 pair initialization, data, optimizer, batches and seeds. Declare same-replay horizon comparisons versus between-asset comparisons. | Dipole matrix | Per-arm lock diff | Not started | YES | OPEN | Invalidate dipole comparison. | Evaluation
G22 | Blind | Freeze October 4/5 outputs plus scoring quantities, groups, exclusions and denominators before the single reveal. No cross-arm access. | All result arms | Immutable output hashes and reveal receipt | Not started | YES | OPEN | Invalidate held-out result. | Evaluation
G23 | Forward shadow | Benefit, calibration, latency, and safe failure reproduce on later live sessions. | Promotion candidate | Time-disjoint shadow report | Not started | YES | OPEN | No live influence. | Operations
G24 | Licensing | DTN/CME confirms MBO fields, retention, AWS topology, and actual non-display categories in writing. | Live data | Vendor response and contract | External | YES | BLOCKED | No live feed purchase/use. | Data/legal
G25 | Safety | Risk gate enforces stale-state, instrument, size, price, position, exposure, and loss limits. | Live execution | Boundary and failure tests | Not started | YES | OPEN | No order submission. | Execution
G26 | Execution | Ledger/reconciler handles acknowledgment, fill, cancel, reject, restart, and ambiguous timeout without blind retry. | Live execution | Sandbox and fault-injection receipts | Not started | YES | OPEN | Freeze new exposure. | Execution

## Sources
Source Register
Repository evidence controls build-state claims. Official external sources support vendor/model/API facts but do not establish market performance or licensing approval.
Source type | Source | Supports | URL/path | Version or inspection note
Repository | Final-candidate record | Recovered B2 target and brownfield lock | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/01_BOSS_FINAL_CANDIDATE_RECOVERY_AND_LOCK.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | Granite assessment | Granite facts, scoring, interface, and promotion gates | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/02_GRANITE_REASONING_LAYER_ASSESSMENT.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | Dipole plan | Control defect, target contract, D0-D5, and four-date test | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/03_DIPOLE_TEACHER_TEST_AND_PROMOTION_PLAN.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | MBO vendor assessment | DTN/CME requirements, costs, and proof-of-capability gate | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/04_LIVE_MBO_VENDOR_AND_COST_ASSESSMENT.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | Execution assessment | Personal automated execution, licensing, risk, and adapters | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/05_PERSONAL_AUTOMATED_EXECUTION_AND_LICENSING.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | AWS governance | Single-user AWS identity, isolation, security, and evidence package | https://github.com/DavisAI1974/Markets/blob/chatgpt/frankie-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss_live_stack/06_AWS_SINGLE_USER_GOVERNANCE.md | Commit 9006b633829cc2d7d34df269d6645d1ec4ddee54
Repository | Accepted BOSS benchmark handoff | A/B0/B1/B2 matrix, four dates, and intended full B2 arm | https://github.com/DavisAI1974/Markets/blob/codex/frankie-boss-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss/FRANKIE_RAW_MBO_BENCHMARK_NEXT_CHAT_HANDOFF_20260828.md | Inspected source tip 38b37c4323a027b21b5ca65627daf294a1481541
Repository | BOSS trunk | B0, temporal graph, GatedDeltaCell, and QSV seam | https://github.com/DavisAI1974/Markets/blob/beb548b86b777dc69bf834950b30cc28000e16ef/research/kalshi/frankie_boss/trunk.py | V1 source pinned at beb548b8; V2 default restoration and bit-identical B0 fixtures verified.
Repository | Dipole teacher | TeacherHead and none/plain_aux/shuffled/random/dipole controls | https://github.com/DavisAI1974/Markets/blob/codex/frankie-boss-raw-mbo-benchmark-20260828/research/kalshi/frankie_boss/teacher.py | Historical source; corrections already present at beb548b. Current package at 17e4b46a: 309 passed, 1 existing CUDA skip.
IBM | Granite 4.2 8B model card | Checkpoint architecture, context, reasoning modes, inference guidance, and license | https://huggingface.co/ibm-granite/granite-4.2-8b | Inspected 2026-09-04
IBM | Granite 4.2 repository | Official model family and usage material | https://github.com/ibm-granite/granite-4.2-language-models | Inspected 2026-09-04
DTN | IQFeed developer information | Windows IQConnect local client and API constraints | https://www.iqfeed.net/dev/ | Inspected 2026-09-04
CME | Market by Order FAQ | Individual-order data versus aggregated book | https://www.cmegroup.com/articles/faqs/market-by-order-mbo.html | Inspected 2026-09-04
Tastytrade | Developer documentation | Broker API, sandbox, and market-data integration | https://developer.tastytrade.com/docs/get-started/ | Inspected 2026-09-04
Kalshi | API documentation | REST, WebSocket, FIX, authentication, and demo surfaces | https://docs.kalshi.com/welcome | Inspected 2026-09-04
Supplied contract | Corrected R3 contract addendum | C19/C20, C15 normalization/state contracts, workbook reconciliation | CLAUDE_BOSS_CONTRACT_ADDENDUM_R3_20260907-1.md | Corrected §1.3 parameter-count contract; §§1–6 govern this batch.
Patch / repository | C15 prefix foundation | Strict record-prefix/checkpoint contracts | 0005-frankie-boss-c15-record-prefix-round3-1.patch | Committed 17e4b46a; 70 prefix tests; package 309 passed, 1 existing CUDA skip.
Local review package | Parallel R3 batch review | Component evidence, remaining blockers, integration boundaries | CODEX_TO_CLAUDE_PARALLEL_R3_REVIEW_20260907.md | Historical review; current native mapping and teacher build status is in NATIVE_MAPPING_BUILD_HANDOFF_20260907.md.
Supplied contract | Granite structured-output plan | Pure schema/parser/reward/evaluator; later prompt, tuning, and identity | BOSS_GRANITE_STRUCTURED_OUTPUT_PLAN_V1_20260907.md | Read with later H2/P7 ruling: evidence_verdict, L4-only metrics, no P6/P7 exceptions. Pure parser/evaluator 126 passed; prompt 55 passed. No model run.
Supplied ruling | H2 and P7 decisions | Batched B1; 1e-4 bound; single-packet serving; evidence_verdict; L4 denominator | parallel_r3_contracts/CLAUDE_TO_CODEX_H2_P7_RULINGS_20260907.md | 2026-09-07; implemented; schema identifier unchanged.
Published code | H2/P7 implementation handoff | Current acceptance, review, remaining integration boundary | https://github.com/DavisAI1974/Markets/tree/9b12aaf1f9b94e0e016364ef02d2b181472812f3 | Branch codex/boss-h2-p7-rulings-20260907; published tip 9b12aaf1. B1 49 / parser-evaluator 126 / prompt 55.
Repository reference files | Pinned dependencies for Claude | trunk.py; causal_packet.py; state_serialization.py; frankie_contract.py | reference_source/research/kalshi/frankie_boss/ | Exact base beb548b86b777dc69bf834950b30cc28000e16ef; SHA-256 and Git blob identities in package manifest.
Supplied full review | Claude parallel R3 memo | R1/R2 required; nonblocking follow-ups and integration notes by component | parallel_r3_contracts/CLAUDE_TO_CODEX_PARALLEL_R3_REVIEW_MEMO_20260907.md | Static review accepts the batch after R1/R2; no broad rerun. Architecture and H2/P7 rulings unchanged.
Published corrections | R3 review corrections | Interior convergence, precise prompt identifiers, eval-mode guard and deferred work | https://github.com/DavisAI1974/Markets/blob/9b12aaf1f9b94e0e016364ef02d2b181472812f3/research/kalshi/frankie_boss/R3_REVIEW_CORRECTIONS_20260907.md | 104 passed: 49 B1 + 55 prompt. Published tree equals tested local tree; commit mapping supplied. No integration or model run.
Owner override | Full-evidence corrections | No silent loss, caps, raw averaging/smoothing or archive-only completion | https://github.com/DavisAI1974/Markets/tree/5e93896dd0dd8238fa3ff2af48a0e086fe42170e | Historical starting commit. Later approved full-evidence ruling restores teacher transforms and finite context without raw loss.
Current handoff | Completed native mapping build | Exact mapping, teacher attachment, context receipts, preservation and focused checks | https://github.com/DavisAI1974/Markets/blob/8ace10f2634687f7456e42f3b5f1ffe6a8724f89/research/kalshi/frankie_boss/NATIVE_MAPPING_BUILD_HANDOFF_20260907.md | Published commit 8ace10f2634687f7456e42f3b5f1ffe6a8724f89. Mapping software complete. Remaining production scope clarified by owner on 2026-09-14. No operational runs.
Current reference files | Approved full-evidence ruling | Granite/trunk restoration, native context and teacher contract | research/kalshi/frankie_boss/CLAUDE_TO_CODEX_FULL_EVIDENCE_RULING_20260907.md | Approved by Greg, with follow-up authorization to fix exact identity/reconstruction gaps.
Published code | Governed QSV attachment | Native artifact/mask consumption and retry identity | https://github.com/DavisAI1974/Markets/blob/25db5c8b6c5e9da2872f1870c77fca82dee1731f/research/kalshi/frankie_boss/QSV_CONTEXT_HANDOFF_20260914.md | Artifact-to-model software built. Producer correctness, production wiring and throughput remain open.
Published code | Rolling forecast software handoff | Best-candidate selection, all-horizon revisions and durable retry intent | https://github.com/DavisAI1974/Markets/blob/ccc7159d97a9bd91368c48f20fa5f453f53e5e5d/research/kalshi/frankie_boss/ROLLING_FORECAST_BUILD_HANDOFF_20260914.md | 871 passed, 1 CUDA-only skip across two processes. Includes 82 new forecast checks. Synthetic software only.
Owner-revised design | Native forecast and confidence specification | No categorical publication bands; ranking, calibration research and fixed-target revisions | https://github.com/DavisAI1974/Markets/blob/ccc7159d97a9bd91368c48f20fa5f453f53e5e5d/research/kalshi/frankie_boss/SPEC-native-forecast-confidence.md | 2026-09-14 owner revision. Native heads and protected confidence compatibility remain pending; no empirical binding or live cadence invented.

## Preservation Audit
BOSS preservation audit — rolling forecast checkpoint
Mapping, QSV attachment and rolling forecast software verified. Native forecast heads, protected integration and production B2_GATED remain incomplete.
Code checkpoint ccc7159d. 871 synthetic checks pass; 1 CUDA-only skip. Training, market-data runs, held-out/OSS evaluation and execution remain parked.
Area | Status | Finding | Correction / next work | Evidence / limitation | Code / authority
Native field mapping | Built - software | No complete native field map existed in the inspected inventories. | Exact registered tensors now reach learned computation; undeclared fields fail. | Per-field sensitivity, inverse reconstruction, causal links and context coverage pass. | native_mbo_encoder.py; context_session.py
C15 retention and IDs | Corrected | Complete raw retention must remain separate from candidate target windows. | Append-only exact journal preserved; every prefix record reaches attached teacher processing. | 15 tests, including 4,200 events and partial IDs. | c15_builder.py; c15_journal.py
Raw reduction | Corrected | Raw evidence must not be clipped, normalized, smoothed or averaged away. | Exact raw lane preserved; approved teacher-only transforms/normalizer restored downstream. | Raw values and all events preserved. | c15_observer.py; c15_teacher.py
Record versions and values | Corrected | Current-fact resolution hid versions; missing fields and float coercion lost evidence. | All as-of versions retained; explicit latest query; presence-aware field_entries and exact values. | Full-history and causal packet regression tests. | causal_packet.py
Packet identity/ownership | Corrected | Mutable payloads and 12-digit hash quantization. | Deep immutable copies and exact typed payload/feature hash bindings. | Mutation, last-bit, signed-zero and int/float identity tests. | causal_packet.py; c15_journal.py
Clock mismatches | Corrected | Received inverted-clock rows excluded; defects not propagated. | All received rows retained with named adapter clock contract and original times; defects reach packets. | Generic clock bypass and future leak tests. | databento_adapter.py; causal_packet.py
Completeness and telemetry | Corrected | Maximum observed time stood in for completeness; stats were reset. | Unknown authoritative watermark degrades; no rescan; all operator fetch diagnostics retained. | Single-scan and telemetry retention tests. | databento_adapter.py
Attention/history access | Corrected per ruling | Full-day tensor replay and changed control defaults were rejected. | Window 128 / QSV off restored; explicit provisional context 4096 with outside-context receipts. | Pinned control, context membership and future-suffix checks pass. | trunk.py; context_session.py
Partial fields/QSV | Corrected at tensor boundary | Missingness must remain distinct from present zero; QSV must remain optional. | Governed QSV artifacts and masks now reach the native runner when enabled. Producer-side conformance and throughput remain pending. | 11 QSV attachment checks; exact ablation and source/retry binding verified. No production proof. | context_qsv.py; context_session.py; test_context_qsv.py
Restart/provenance | Built - software | History tails, packet membership and actual model identity needed binding. | Forecast refresh intent binds full targets, source, arm, generation, cadence and material flag before generation. Original context restart retained. | 82 forecast checks include selection, immutable revisions and changed-intent rejection after failure/restart. | rolling_forecast.py; forecast_refresh.py; forecast_confidence.py
Readable numeric state | Corrected | 12-digit rounding, int-to-float loss and silently zipped QSV extras. | Serializer v2 exact types/digits, signed zero, explicit clock domains and strict widths. | Round-trip, underflow and extra-field tests. | state_serialization.py
Granite output | Corrected | Response caps constrain assistance, not raw evidence retention. | Approved V1 output/prompt restored; nonempty hypotheses and reference rules retained. | 195 focused Granite/precision checks pass. | granite_output_schema.py; granite_prompt.py
Protected Frankie | Preserved | Existing activity windows and compact frames are reductions in the original path. | Existing adapter/replay/calculations/BLD-1 unchanged; C15 preserves raw evidence separately. | Protected code unchanged. Category-free ranking is separate from legacy BLD-1 confidence; enabled compatibility and disabled proof remain. | frankie_contract.py; c15 tests
Neural/evaluation arithmetic | Explicit boundary | LayerNorm, softmax, learned memory and experimental metric averages still exist. | Not silently removed as though they were data-retention settings. Research evaluations remain parked. | No claim that every average/limit vanished from repository. | trunk.py; teacher.py; granite_evaluation.py
Historical restoration | Not a live-data recovery | No real market data was run through the abandoned capped draft. | No live dataset was restored; an external recovery needs original source members/receipts. | Synthetic data only in this correction. | FULL_EVIDENCE_HANDOFF_20260907.md
Operational runs | Parked by owner | Build completion does not authorize training, market-data or OSS runs. | No Frankie, training, provider, market-data, mechanics or OSS launch. | Synthetic software checks only; original optional training test remains. | ROLLING_FORECAST_BUILD_HANDOFF_20260914.md